## Sheet1
ARPA Projects County
[6 empty] | M&O - 54455 | M&O- 54455 | M&O | CAPITAL-55370 | Construction Start | Construction Complete | Status
Approval Date | Project # | Project Description | ARPA Cost Center | Original Fee | Increased Fee | OWNER'S REP FEE | DESIGN FEE | Other | CONSTRUCTION $
2022-08-15 | 10009 | Juvenile Justice Elevator | 373 | 538898 | 1746677.6 | 51920 | 60000 |  | 1634757.6 | 2024-08-01 | 2025-12-30 | Work Contracted KONE
2022-08-15 | 10031 | Juvenile Justice Lobby | 373 | 955000 | 1146000 | 118660 | 0 | 645500 | 381840 | 2023-10-01 | 2024-06-01 | construction complete
2022-12-05 | 10033 | 5th Floor Re-model | 373 | 9860000 | 6360000 | 280700 | 220000 | 1460213 | 4399087 | 2024-03-04 | 2026-10-30 | Awarded
2022-12-05 | 10035 | Court Clerk Jury Pavillion | 373 | 250000 | 250000 | 26160 | 0 |  | 223840 |  |  | Cancelled
2022-06-21 | 10046 | OCSO Midwest City Substation HVAC | 372 | 525000 | 546340 | 21340 | 0 | 477600 | 47400 | 2024-01-01 | 2024-06-01 | Construction Complete
10/20/2022 & 11/17/2022 | 10067 | Clerks Books project 1st Floor | 373 | 125000 | 150000 | 15230 | 0 |  | 134770 | 2023-11-13 | 2024-11-01 | Demo Complete
10/20/2022 & 11/17/2022 | 10067 | Annex 3rd Floor Purchasing | 373 | 175000 | 210000 | 18930 | 0 | 168959.4 | 22110.6 | 2022-09-01 | 2023-09-30 | Closed out
2022-08-15 | 10067 | Annex Security/Front Entrance | 373 | 1000000 | 1878945.4 | 115070 | 0 |  | 1763875.4 | 2024-06-01 | 2025-06-30 | Contracted Cooley
2022-12-05 | 10068 | Drainage Culvert Inventory | 372 | 1500000 | 1500000 | 19250 | 0 | 1480750 | 0 | 2023-05-01 | 2024-12-30 | work underway 90% complete
2022-08-15 | 10095 | Juvenile Justice Roof | 373 | 914683 | 1097619.6 | 46040 | 0 | 856369.04 | 195210.56 | 2023-08-01 | 2024-07-01 | Construction complete
2022-12-05 | 10117 | Camera Security System (County) | 372 | 583951.24 | 640691.24 | 12240 | 0 |  | 628451.24 | 2023-03-15 | 2023-09-30 | Closed out
2022-12-05 | 10119 | Courthouse Elevator (Jail) | 373 | 1560000 | 1560000 | 89710 | 135000 |  | 1335290 | 2024-11-01 | 2025-12-30 | Work Contracted KONE
2022-12-05 | 10120 | Annex Elevators | 373 | 6420000 | 6420000 | 141680 | 435000 |  | 5843320 | 2025-01-01 | 2026-10-30 | Work Contracted KONE
2023-01-03 | 10130 | Behavioral Health Services Facility | 373 | 40000000 | 40000000 | 1039620 |  |  | 38960380 | 2025-01-01 | 2026-12-30 | not started
| 10073 | Existing Jail HVAC |  |  | 136500 | 136500 |  |  | 5500000 | 2024-08-01 | 2025-08-01 | Contracted United Mech
2023-03-20 | 10074 | Existing Jail Roof Replacement |  |  | 480000 | 16800 |  | 219160.27 | 244039.73 | 2024-03-01 | 2024-08-01 | Construction complete
| 10077 | Existing Jail Loading Dock |  |  | 164400 | 9980 |  | 149000 | 5420 | 2024-04-01 | 2024-11-01 | Construction nearing completion
2023-03-20 | 10078 | Existing Jail Metal Roof Repair |  |  | 30000 | 1000 |  | 11108.45 | 17891.55 | 2024-03-01 | 2024-08-01 | Construction complete
|  | Sub-Total |  | 64407532.24 | 64317173.84 | 2160830 | 850000 | 5468660.16 | 61337683.68
Sub Recipiant Projects PBA
2022-12-05 | 10117 | Camera Security System (PBA) | 365 | 492258.01 | 500678.01 | 8420 | 0 | 492258.01 | 0 | 2023-09-01 | 2024-10-01 | Installation underway
2022-12-05 | 10121 | ICB Elevator | 365 | 1600000 | 1600000 | 65790 | 107500 |  | 1426710 | 2024-12-01 | 2026-12-30 | Contracted KONE
2022-12-05 | 10122 | Metro 1 Elevator | 365 | 1600000 | 1600000 | 74860 | 107500 |  | 1417640 | 2024-12-01 | 2025-12-30 | Contracted KONE
2022-12-05 | 10123 | Metro 2 Elevator | 365 | 1600000 | 1600000 | 89260 | 100000 |  | 1410740 | 2024-12-01 | 2025-07-30 | Contracted KONE
2022-08-15 | 10064 | Krowse - Emergency Op Center | 365 | 5080000 | 6168000 | 458650 | 683000 |  | 5026350 | 2024-09-01 | 2025-12-30 | Work underway
| 10133 | DA transition to ICB | 365 | 3500000 | 3500000 | 245000 | 175000 |  | 3080000 | 2024-10-01 | 2026-02-01 | Construction Documents
|  | Sub-Total |  | 13872258.01 | 14968678.01 | 941980 | 1173000 | 492258.01 | 12361440
[5 empty] | TOTAL CONSTRUCTION BUDGET | TOTAL OWNER'S REP | TOTAL DESIGN |  | TOTAL CONSTRUCTION
[5 empty] | 79285851.85 | 3102810 | 2023000 | 5960918.17 | 73699123.68