BOCC Project listing and status update

William White and Associates, LLC

December 9, 2024

|  | Juvenile Justice Elevator - #10009 - Kone proceeding with submittals. - Schedule – within all required guidelines |  |
| --- | --- | --- |
|  | Court Clerk Social Distancing - #10033 – 5th Floor - Contract award complete – budget available for asbestos abatement and change order requirements. - Schedule – subject to project design changes, but completion scheduled for February 2026. |  |
| Clerks Books 1st Floor - #10067 A - Phase one south side complete with punch list items remaining. - Final layout for Clerks Books completed. - North side completion requirement of January 30, 2025. White does not have a schedule update. - Schedule – within all required ARPA guidelines |  |  |
| Annex Security/Front Entrance - #10067 C - Work has started on the exterior and first phase on the interior. - Schedule – within all required guideline |  |  |

Drainage Culvert Inventory - #10068

- Culvert review is almost 95% complete and on schedule for late December 2024 completion.

- Currently reviewing and correcting some QC issues and making final surveys.

- Schedule – within all required guideline

| Courthouse Elevator (Jail) - #10119 - Kone was selected as contractor. Contract has been issued. - Submittal process ongoing. - Schedule – within all required guideline |  |
| --- | --- |
| Annex Elevators - #10120 - Kone selected as contractor. Contract has been issued. - Submittal process ongoing. - Schedule – within all required guideline |  |
| Behavioral Health Services Facility - #10130 |  |

- Site selected.

- Contractor selection complete.

- Land purchased and continuing plan review.

- January 2, 2025, start date. CMAR contract in review.

- Schedule – Current project schedule concerns.

Existing Jail HVAC - #10073

- Work progressing.

- Schedule – within all required guideline

Existing Jail Loading Dock - 10077.

- Contractor complete.