## Sheet1
Capital Projects Schedule
Project On-Going | Design Start Date | Design Fees | Construction Start Date | Construction Fees | Construction Fees With Changes Orders | Anticipated Completion Date | Funding Source | Other
Oklahoma County Sheriff Office | 2023-02-01 | 508637 | 2024-11-01 | 12491363 |  | 2026-11-01 | PBA, Bond
Annex 6th Floor Incidentals | NA | NA | 2023-01-01 | 50000 |  | 2024-08-01 | General Fund | HVAC Part
Annex HVAC | 2013-07-01 | 280000 | 2014-01-01 | 2029692 | 2095591.47 | 2026-06-01 | TIF | Pre Funded
Annex 3rd Floor Treasurer | 2022-09-22 | 18000 | 2022-09-01 | 231600 |  | 2024-10-01 | Treasurer
Sub-Total |  |  |  | 14802655
Project Anticipated | Anticipated Design Start Date | Anticipated Design Fees | Anticipated Construction Start Date | Anticipated Construction Fees |  | Anticipated Completion Date | Anticipated Funding Source | Other
PBA
Metro 1 Garage | 2022-08-22 | 17000 | 2025-07-01 | 275000 |  | 2025-12-01 | PBA
Metro 2 Garage | 2022-08-22 | 17000 | 2026-01-01 | 275000 |  | 2026-12-01 | PBA
ANNEX
Annex Security/West Columns | 2020-10-01 | 19220 | 2025-07-01 | 100000 |  | 2025-12-01 | General Fund | TIF Eligible Reimbursement
Annex Security/ North Curb | 2020-10-01 | 27480 | 2025-07-01 | 200000 |  | 2025-12-01 | General Fund | TIF Eligible Reimbursement
Annex Fire Detection and Alarm upgrade | TBD |  |  | 115000 |  |  | General Fund | TIF Eligible Reimbursement
Annex Emergency Lighting | TBD |  |  | 55000 |  |  | General Fund | TIF Eligible Reimbursement
COURTHOUSE
Egress 11th Floor | 2021-12-01 | 64000 | 2025-01-02 | 444000 |  | 2025-12-01 | General Fund, PBA | TIF Eligible Reimbursement
9th Floor HVAC | 2025-03-01 | 35000 | 2025-11-01 | 900000 |  | 2026-06-01 | PBA
ICB
ICB Rehab | 2023-10-01 | 795000 | 2025-01-01 | 14000000 |  | 2026-12-01 | ARPA, PBA | TIF Eligible Partial Reimbursement
JJC
JJC New Courtrooms | 2025-01-01 | 125000 | 2025-07-01 | 7000000 |  | 2026-07-01 | PBA
NEW
Oklahoma County Detention Center | 2023-08-01 | 23233155 | 2025-07-01 | 230000000 |  | 2028-09-01 | County Bond
Sub-Total |  |  |  | 268398255
Archived
secuity turnstile |  |  |  | 110000
Annex Roof Drains |  |  |  | 224000
Annex Wellness Center |  |  |  | 40000
Annex Crossover Elevator |  |  |  | 1900000
County Records Storage Facility |  |  |  | 5000000
Lincoln Parking Lot |  |  |  | 300000
Lincoln Building Marquis |  |  |  | 75000
Metro I Elevator Badge Access |  |  |  | 50000
ICB Roof |  |  |  | 250000
Sub-Total |  |  |  | 7949000

## Sheet2
Infrastructure Projects
Funding Watch
PROJECT | BUDGET | ANTICIPATED COST | SHORTAGE | NOTES
Investor Capital Building | 10000000 | 14000000 | -4000000 | Some potential funding available
4 pipe HVAC, Stairs, Str. Bracing |  |  |  | in PBA accounts, TIF accounts.
District Court Courtrooms | 2000000 | 7000000 | -5000000
at JJC
Metro Elevator Generator | 0 | 550000 | -550000
JJC elevator upgrade | 535000 | 835000 | -300000
Change Order $ all bid elevators | 0 | 500000 | -500000
Courthouse 9th Floor HVAC | 0 | 900000 | -900000
Sub-Total |  |  | -11250000
New Jail Construction | 230000000 | 610000000 | -380000000